## Group Planner
| Task | Name | 2016-03-15 | 2016-03-17 | 2016-03-21 | 2016-03-23
◻ | Create 2 more boss sprites | Grant |  | X
◻ | Create 4 enemy sprites | Grant |  |  | X
◻ | Create scenery sprites | Grant |  |  |  | X
◻ | Create alternate player models | Cole |  |  | X
◻ | Research new IDE | Jake | X
◻ | Research graphic libraries | Jake |  | X
◻ | Event timeline | Cole |  |  | X
◻ | Research similar games | Cole |  | X
◻ | Reseach sound libraries | Jake |  | X
◻ | Implement new IDE and libraries | Jake |  |  | X
◻ | Brainstorm new names | Grant, Cole, Jake |  |  |  | X
◻ | Make sounds | Cole |  |  |  | X
◻ | Compose music | Cole |  |  |  | X
◻ | Begin Mechanical Code | Jake |  |  |  | X
◻ | Optimize class design | Jake |  |  |  | X
◻
◻
◻
◻
◻
◻
◻
◻
◻
◻
◻
◻
◻
◻
◻
◻
◻
◻
◻
◻
◻
◻
◻
◻
◻
◻
◻
◻
◻
◻
◻
◻
◻
◻
◻
◻
◻
◻
◻
◻
◻

## Sample Duties
| Task | Name | 2016-03-15 | 2016-03-17 | 2016-03-21 | 2016-03-23
◻ | Initiate | Bill of Materials Template
◻ | Initiate | Business Case
◻ | Initiate | Business Rules
◻ | Initiate | Needs Statement
◻ | Initiate | Concept Proposal
◻ | Initiate | Scope of Work
◻ | Initiate | Statement of Work
◻ | Concept Development | Cost Benefit Analysis
◻ | Concept Development | Feasibility Study
◻ | Concept Development | Risk Management Plan
◻ | Concept Development | System Boundary Document
◻ | Planning | Acquisition Plan
◻ | Planning | Availability Plan
◻ | Planning | Capacity Plan
◻ | Planning | Change Management Plan
◻ | Planning | Concept of Operations
◻ | Planning | Configuration Management Plan
◻ | Planning | Project Plan
◻ | Planning | Quality Assurance Plan
◻ | Planning | Security Plan
◻ | Planning | Transition Plan
◻ | Planning | Verification & Validation Plan
◻ | Requirements Analysis | Business Requirements
◻ | Requirements Analysis | Functional Requirements
◻ | Requirements Analysis | Interface Control Document
◻ | Requirements Analysis | Software Requirements Specification
◻ | Requirements Analysis | System Specifications
◻ | Requirements Analysis | Test Plan
◻ | Design | Conversion Plan
◻ | Design | Database Design Document
◻ | Design | Design Document
◻ | Design | System Design
◻ | Design | User Guide
◻ | Development | Contingency Plan
◻ | Development | Software Development Plan
◻ | Test | Acceptance Test Plan
◻ | Test | Change Control Form / Logs
◻ | Test | Change Request Form
◻ | Test | Quality Log
◻ | Test | Risk Log
◻ | Test | Test Script
◻ | Test | Test Tracking Report
◻ | Test | Test Case
◻ | Test | Test Problem Record
◻ | Test | Unit Test
◻ | Test | User Acceptance Test Plan
◻ | Implementation | Deployment Plan
◻ | Implementation | Implementation Plan
◻ | Implementation | Installation Plan
◻ | Implementation | Release Notes
◻ | Implementation | Request For Change Form
◻ | Operations and Maintenance | Maintenance Plan
◻ | Operations and Maintenance | Operations Guide
◻ | Operations and Maintenance | System Administration Manual
◻ | Operations and Maintenance | Setup Guide
◻ | Disposition | Disposition Plan

## Sample Gantt Chart
Sample Project Plan: System Selection
Project name:
Ref | Tasks | Responsibility | Start | End | Days | 2015-06-01 |  |  |  |  | 2015-06-08 |  |  |  |  | 2015-06-15 |  |  |  |  | 2015-06-22 |  |  |  |  | 2015-06-29 |  |  |  |  | 2015-07-06 |  |  |  |  | 2015-07-13 |  |  |  |  | 2015-07-20 |  |  |  |  | 2015-07-27 |  |  |  |  | 2015-08-03 |  |  |  |  | 2015-08-10 |  |  |  |  | 2015-08-17 |  |  |  |  | 2015-08-24 |  |  |  |  | 2015-08-31
|  |  | Date | Date | time axis 2015-06-01 to 2015-09-04
1 | Requirements specification |  | 2015-06-01 | 2015-06-17 | bar: 2015-06-01 to 2015-06-17
1.1 | User interviews / use Axia Template | U, IT | 2015-06-01 | 2015-06-11 | 9 | bar: 2015-06-01 to 2015-06-11
1.2 | Consolidate requirements | U, IT | 2015-06-10 | 2015-06-12 | 3 | bar: 2015-06-10 to 2015-06-12
1.3 | 1st draft of requirements | U | 2015-06-12 | 2015-06-12 | 1 | bar: 2015-06-12
1.4 | Review and amend requirements | U | 2015-06-15 | 2015-06-16 | 2 | bar: 2015-06-15 to 2015-06-16
1.5 | Sign off requirements | M, PS | 2015-06-17 | 2015-06-17 | 1 | bar: 2015-06-17
2 | RFI (Request for Information) |  | 2015-06-15 | 2015-06-19 | bar: 2015-06-15 to 2015-06-19
2.1 | Identify possible software, vendors | IT, U | 2015-06-15 | 2015-06-16 | 2 | bar: 2015-06-15 to 2015-06-16
2.2 | Prepare RFI | IT, U | 2015-06-16 | 2015-06-18 | 3 | bar: 2015-06-16 to 2015-06-18
2.3 | Contact vendors / issue RFI | IT | 2015-06-19 | 2015-06-19 | 1 | bar: 2015-06-19
3 | Short list software, vendors |  | 2015-06-25 | 2015-07-01 | bar: 2015-06-25 to 2015-07-01
3.1 | Review & analyse RFI responses | IT, U | 2015-06-25 | 2015-06-29 | 3 | bar: 2015-06-25 to 2015-06-29
3.2 | Compare against requirements | IT, U | 2015-06-26 | 2015-06-30 | 3 | bar: 2015-06-26 to 2015-06-30
3.3 | Identify short list of 3 or 4 vendors | IT, U | 2015-07-01 | 2015-07-01 | 1 | bar: 2015-07-01
3.4 | Inform vendors of status | IT | 2015-07-01 | 2015-07-01 | 1 | bar: 2015-07-01
4 | Systems demonstrations |  | 2015-06-22 | 2015-07-08 | bar: 2015-06-22 to 2015-07-08
4.1 | Arrange with short listed vendors | IT | 2015-07-01 | 2015-07-01 | 1 | bar: 2015-07-01
4.2 | Create demo scripts / questions | U, IT | 2015-06-22 | 2015-06-24 | 3 | bar: 2015-06-22 to 2015-06-24
4.3 | Attend demonstrations | U, IT | 2015-07-06 | 2015-07-07 | 2 | bar: 2015-07-06 to 2015-07-07
4.4 | Review findings | U, IT | 2015-07-08 | 2015-07-08 | 1 | bar: 2015-07-08
4.5 | Reduce short list to 2 or 3 vendors | U, IT | 2015-07-08 | 2015-07-08 | 1 | bar: 2015-07-08
5 | Refine new system design thoughts |  | 2015-07-01 | 2015-07-09 | bar: 2015-07-01 to 2015-07-09
5.1 | Additional design thoughts | U, IT | 2015-07-01 | 2015-07-02 | 2 | bar: 2015-07-01 to 2015-07-02
5.2 | Details from systems demonstrated | U, IT | 2015-07-06 | 2015-07-08 | 3 | bar: 2015-07-06 to 2015-07-08
5.3 | Revise system design | U, IT | 2015-07-09 | 2015-07-09 | 1 | bar: 2015-07-09
6 | RFP (Request for proposal) |  | 2015-06-25 | 2015-07-22 | bar: 2015-06-25 to 2015-07-22
6.1 | Prepare RFP | IT, U | 2015-06-25 | 2015-07-01 | 5 | bar: 2015-06-25 to 2015-07-01
6.2 | Issue to short listed vendors | IT | 2015-07-13 | 2015-07-13 | 1 | bar: 2015-07-13
6.3 | Review, analyse, score responses | IT, U | 2015-07-20 | 2015-07-22 | 3 | bar: 2015-07-20 to 2015-07-22
7 | Further investigations |  | 2015-07-23 | 2015-08-06 | bar: 2015-07-23 to 2015-08-06
7.1 | Prototyping | IT, U | 2015-07-23 | 2015-08-05 | 10 | bar: 2015-07-23 to 2015-08-05
7.2 | Test system | IT, U | 2015-07-27 | 2015-07-30 | 4 | bar: 2015-07-27 to 2015-07-30
7.3 | Queries from RFP responses | IT, U | 2015-07-30 | 2015-08-03 | 3 | bar: 2015-07-30 to 2015-08-03
7.4 | Hardware, network, database | IT | 2015-08-04 | 2015-08-06 | 3 | bar: 2015-08-04 to 2015-08-06
8 | Detailed system demonstrations, vendor discussions |  | 2015-08-10 | 2015-08-14 | bar: 2015-08-10 to 2015-08-14
8.1 | Cover all points from 6, 7 above | IT, U | 2015-08-10 | 2015-08-14 | 5 | bar: 2015-08-10 to 2015-08-14
8.2 | Resovle outstanding queries, issues | U, IT | 2015-08-10 | 2015-08-14 | 5 | bar: 2015-08-10 to 2015-08-14
9 | Reference site visits |  | 2015-08-11 | 2015-08-18 | bar: 2015-08-11 to 2015-08-18
9.1 | Identify who to visit | U, IT | 2015-08-11 | 2015-08-11 | 1 | bar: 2015-08-11
9.2 | Determine agenda | U, IT | 2015-08-11 | 2015-08-12 | 2 | bar: 2015-08-11 to 2015-08-12
9.3 | Arrange visits | U | 2015-08-12 | 2015-08-12 | 1 | bar: 2015-08-12
9.4 | Attend visits | U, IT | 2015-08-17 | 2015-08-18 | 2 | bar: 2015-08-17 to 2015-08-18
9.5 | Contact other sites by phone | U | 2015-08-13 | 2015-08-13 | 1 | bar: 2015-08-13
10 | Decision |  | 2015-08-19 | 2015-09-04 | bar: 2015-08-19 to 2015-09-04
10.1 | Pull all results & findings together | PM, M, IT, U | 2015-08-19 | 2015-08-21 | 3 | bar: 2015-08-19 to 2015-08-21
10.2 | Prepare proposal paper | PM, PS | 2015-08-24 | 2015-08-25 | 2 | bar: 2015-08-24 to 2015-08-25
10.3 | Board / steering group meeting | B, SG, PS | 2015-09-03 | 2015-09-03 | 1 | bar: 2015-09-03
10.4 | Decision made | B, SG, PS | 2015-09-03 | 2015-09-03 | 1 | bar: 2015-09-03
10.5 | Inform vendors | PM | 2015-09-03 | 2015-09-03 | 1 | bar: 2015-09-03
10.5 | Final contract, SLA negotiation | P, PM | 2015-09-04 | 2015-09-04 | 1 | bar: 2015-09-04
11 | Project management |  | 2015-06-01 | 2015-09-04 | bar: 2015-06-01 to 2015-09-04
11.1 | Project plan | PM | 2015-06-01 | 2015-06-01 | 1 | bar: 2015-06-01
11.2 | Project kick-off meeting | PM, ALL | 2015-06-01 | 2015-06-01 | 1 | bar: 2015-06-01
11.3 | Weekly progress meetings | PM, U, IT | 2015-06-01 | 2015-09-04 | 14 | bar: 2015-06-08; 2015-06-15; 2015-06-22; 2015-06-29; 2015-07-06; 2015-07-13; 2015-07-20; 2015-07-27; 2015-08-03; 2015-08-10; 2015-08-17; 2015-08-24; 2015-08-31; 2015-09-04
Key
PS = project sponsor
PM = project manager
IT = IT staff
U = users
M = manager (user)
P = procurement
B = board
SG = steering group